## Active TOs
Responsive Strategic Sourcing for Services (RS3) Contract Action(s) Status Report
As of: 03/27/2025
RS3 Requirement # | Requirement Contract History | Requirement Value | Anticipated PoP | Contracting Organization | KO/KS Team | Current Status | KO/MP Response: Yes or No | Sole Source or Competitive Acquisition | Set Aside | Projected RFP Release Date | Projected QTR/FY Award Date | Awarded Contract/Task Order | Mission Partner Organization/Command | Requirement Title | Requirement Synopsis
RS3-23-0049 | Follow-on: W15P7T-17-D-0148, TO-W909MY20F0001 GENERAL DYNAMICS GLOBAL FORCE, LLC | Over $250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-Ft. Belvoir Contracting Team | KO: Rosetta Russell-Wisdom KS: Jessica Hawkins & Mary Suda | Evaluation | Yes (KO) | Competitive Acquisition | Unrestricted | 2024-06-03 | 2025-04-28 | — | Program Executive Office – Intelligence, Electronic Warfare & Sensors (PEO IEWS); Terrestrial Sensors (TS) | Integrated Base Defense – Sustainment Support (IBD-SS) | Product Manager Force Protection Systems (PM FPS) and Product Manager Ground Sensors (PM GS) have requirements for comprehensive training, contractor logistics, operator and sustainment support services, to include material procurement, for equipment and capabilities in both CONUS and OCONUS. The effort requires an innovative program management approach to integrate multiple product support activities to include spares, warehousing/kitting management, maintenance, transportation, shipping, fielding, equipment operator training, contractor equipment operators, field service representatives (FSRs), helpdesk, systems engineering, supplier and total asset visibility management of Integrated Base Defense (IBD) and Force Protection (FP) Family of Systems (FOS). The effort’s performance objective is to achieve cost savings and improved readiness and sustainment support through consolidated support services.
RS3-24-0001 | Follow-on: W15P7T-17-D-0125, TO-W56KGY21F0069 QED SYSTEMS LLC | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC - Division C Contracting Division | KO: Aaron H. Kazi KS: Rachel Polk | Evaluation | Yes (KO) | Competitive Acquisition | Restricted | 2024-09-20 | 2025-04-30 | — | PEO IEWS: PM PNT | PM Positioning, Navigation and Timing (PNT) Product Support Services (PSS) Follow-on Effort | Acquire logistics/product support services for the entire PM PNT portfolio which includes Mounted Assured Positioning, Navigation and Timing System (MAPS); Dismounted Assured Positioning, Navigation and Timing System (DAPS); Resiliency and Software Assurance Measures (RSAM) program; and Positioning, Navigation and Timing Modernization (PNT Mod). Product Support Services (PSS) will be needed in CONUS and OCONUS locations as required.
RS3-24-0002 | Follow-on: W15P7T-19-D-0068, TO-W91CRB20F0013 JANUS RESEARCH GROUP, LLC | $100M-<$150 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC - Division D Contracting Division | KO: Lisa Yamakawa KS: Kelsey Collins | Evaluation | Yes (KO) | Competitive Acquisition | Restricted | 2024-05-06 | 2025-04-21 | — | PEO SOLDIER; HQ PEO SOLDIER | PEO Soldier HQ SETA | Systems Engineering and Technical Assistance (SETA) support to PEO Soldier Headquarters located at Ft. Belvoir, Virginia.
RS3-24-0006 | Follow-on: W15P7T-17-D-0145, TO-W91CRB19F0249 DCS CORPORATION | Over $250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division D Contracting Team | KO: Teresa Quick KS: Liesel Pattee | Evaluation | Yes (KO) | Competitive Acquisition | Unrestricted | 2024-08-14 | 2025-05-15 | — | PEO SOLDIER | Project Manager Soldier Survivability SETA | Support requirements include engineering, quality assurance and test support, acquisition support, business management support, logistics and fielding support, operations support and administrative support. Specific task areas include but are not limited to tasks for program management analysis, planning, studies, liaison and operations support; strategic communications, engineering and logistics support; new equipment training; system test and product fielding support; acquisition and contracting support; software development and system safety, studies and analysis and quick response support. Contractor shall provide support for all phases of system life cycle management to include Technology Maturation and Risk Reduction, Engineering and Manufacturing Development, Production and Deployment, and Operations and Support for PM SSV products. Support also includes program/project management support in response to the deployment and support of PM SSV assets to military requirements worldwide.
RS3-24-0007 | Follow-on: RS3-19-0081: W15P7T-19-D-0157, TO-W56KGU20F0012 RS3-21-0004: W15P7T-19-D-0157, TO-W56KGU21F0013 CACI TECHNOLOGIES, LLC | Over $250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Team | KO: Tammy Woodard KS: Kim Johnston | Pre-Award/Package Development | Yes (KO) | Competitive Acquisition | Unrestricted | 2025-04-23 | 2025-07-22 | — | Combat Capabilities Development Command (DEVCOM) Armaments Center | Field, Lab and Air Integration / Experimentation / Modeling / Simulation / Analysis and Risk Reduction (FLAIR) | Contractor shall provide the engineering, technical, and administrative services and material to perform the collective missions of the DEVCOM C5ISR Center Lab and Field Risk Reduction (LFRR) Division and the Air Integration and Engineering (AI&E) Division. These organizations fall under the Army Futures Command and are tasked with delivering innovative technical solutions to meet the Army's Modernization Priorities.
RS3-24-0012 | New Requirement | $100M-<$250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division C Contracting Division | KO: Oral Grant KS: Patrick Cruickshank and Amber Lowe | Solicitation | Yes (KO) | Competitive Acquisition | Restricted | 2025-03-26 | 2026-01-30 | — | PEO IEWS | PM Cyber & Space SETA Contract | Mission Requirement: SETA services to include programmatic/business management services, engineering support services and acquisition/administrative support services to augment PM C&S core Government personnel and turn-key solutions to support the missions of PM C&S and its associated PdMs and customers.
RS3-24-0025 | Follow-on: FA873215D0044, TO-FA489021F0010 CACI NSS, INC. | $100M-<$250 Million | Six-year PoP, Base and Five Options | External Package, being worked by ACC AMIC Contracting Division | KO: Christina M. Crawley KS: Pat Lucas | Evaluation | Yes (KO) | Competitive Acquisition | Restricted | 2024-11-12 | 2025-05-13 | — | Air Combat Command (ACC) Acquisition Management & Integration Center (AMIC) | Network Operations and Security Center (NOSC) Information Technology (IT) Support Services | The USAFCENT NOSC executes the full-spectrum of information technology (IT) management services and operations for USAFCENT networks 24/7, and is tasked by USCENTCOM to provide information assurance (IA), boundary intrusion detection and intrusion prevention for USCENTCOM components. Comprised of NOSC operations, operations support, cybersecurity, network engineering and command support functions, the USAFCENT NOSC plans, engineers, installs, integrates, operates and maintains, protects and manages enterprise-wide network and systems architecture, infrastructure and services, and provides enterprise-level oversight to its subordinate and supported communications support activities.
RS3-24-0026 | New Requirement | $100M-<$250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-RSA Contracting Division | KO: Gina Petrino KS: Jason Underwood | Package Received | Yes (KO) | Competitive Acquisition | Unrestricted | 2025-04-04 | TBD | — | PEO IEWS; Tactical Space Superiority (TSS) | Integrated Product Support for Tactical Integrated Ground Suite (TIGS) | Contractor shall provide services to support the Tactical Integrated Ground Suite (TIGS) Family of Systems (FoS) for Integrated Product Support (IPS), Material Fielding, Platform Integration and Field Support Services. These services comprise the full spectrum of Integrated Product Support in a global environment and are IAW Army Regulation (AR) 700-127 and Department of the Army Pamphlet (DA PAM) 700-127. Applicable IPS elements for TIGS support include Product Support Management; Design Interface; Sustaining Engineering; Maintenance Planning; Management; Supply Support; Technical Data; Training and Training Support; Systems Continuous Support; Facilities and Infrastructure Support; Packaging, Handling, Storage and Transportation; Manpower and Personnel.
RS3-24-0030 | Follow-on: W15P7T-17-D-0133, TO-W15P7T20F0035 (RS3-18-0077) SIGMATECH, INC. | $100M-<$250 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: John Harvey KS: Kaitlyn Harward | Solicitation | Yes (KO) | Competitive Acquisition | Restricted | 2025-02-15 | 3rd QTR / FY 2025 | — | AMCOM - Army Aviation and Missile Command Directorate: AMCOM Field Maintenance Directorate (AFMD) | AMCOM Field Maintenance Directorate (AFMD) | Contractor shall provide technical, engineering, logistical and materials support for design, development, fabrication, kitting, CONUS/OCONUS fielding, operation, maintenance, modification, upgrade, refurbishment, repair and life-cycle support for electronic systems, missile systems and subsystems; Electronic communication systems and subsystems; Automated Test Equipment (ATE); Test Program Sets (TPSs); Test Measurement and Diagnostic Equipment (TMDE); standard and non-standard Army Aviation Support Equipment and associated hardware. Contractor shall provide overall maintenance support for these systems, to include all levels of maintenance for both field and sustainment. This mission requirement also includes the logistics, sustainment and maintenance support to the Theater Aviation Maintenance Program (TAMP) Equipment Package (TEP).
RS3-24-0033 | Follow-on: W15P7T-17-D-0155, TO-W15P7T21F0004 AMENTUM SERVICES, INC. | $25M-<$50 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: Jeannette Brush KS: Luis Del La Cruz | Pre-Award/Package Development | Yes (KO) | TBD | TBD | TBD | TBD | — | US Navy Program Executive Officer for Unmanned Aviation and Strike Weapons (PEO (U/W) PM/PdM/PdL Directorate - Aerial Targets Program Office (PMA-208) | Technical Services in Support of Naval Air Systems Command Multi-Service Targets and Ranges | Contractor shall provide engineering and logistics services necessary for the support of Program Executive Officer for Unmanned Aviation and Strike Weapons (PEO (U/W), Aerial Targets Systems Program Office (PMA-208) and Naval Air Warfare Center Weapons Division (NAWC-WD) Point Mugu/China Lake supporting multi-service target, range and training programs at various Navy and DoD installations. The Program Executive Officer for Unmanned Aviation and Strike Weapons (PEO (U/W), Aerial Targets Program Office (PMA-208) is responsible for providing threat representative aerial target systems in support of weapon systems test and fleet training. In executing these responsibilities, PMA-208 exercises full acquisition life-cycle management responsibilities encompassing the development, testing, procurement and sustainment of various target systems in support of multiple services within Department of Defense (DoD).
RS3-24-0038 | Follow-on: W15P7T-17-D-0146, TO-W15P7T19F0499 IAP Worldwide Services, Inc | $25M-<$50 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: Sharon Joyner KS: Daniela Miller | Pre-Award/Package Development | Yes (KO) | Competitive Acquisition | TBD | TBD | 2025-06-21 | — | TACOM Clothing and Heraldry (C&H) Product Support Integration Directorate (PSID) Central Management Office (CMO) | Non-Destructive Test Equipment (NDTE) System Support | Contractor shall establish and maintain field operating teams who will operate and maintain the Non-Destructive Test Equipment (NDTE) System. The NDTE System is a portable, deployable self-contained system that detects physical or structural defects in body armor plates worn by Soldiers. The NDTE system consists of an Armor Inspection System (AIS) which employs an X-ray to scan body armor plates [(Enhanced Small Arms Protective Insert (ESAPI), X-Threat Small Arms Protective Inserts (XSAPI), Enhanced Side Ballistic Insert (ESBI) Plates, X-Threat Side Ballistic Insert (XSBI)]. The NDTE System scans for physical or structural defects in the ceramic materials, as well as flaws within the composite laminate or the bonds between the ceramic and composite that are undetectable by visual inspection. The inspection component can be used as a stand-alone system in an environmentally controlled facility. It can also operate as a self-contained unit within a Hard-Sided Expandable Light Air Mobile Shelter (HELAMS). The NDTE System is capable of scanning a plate in 15 seconds or less and can scan as many as 240 plates in one hour. In addition to plate X-ray inspections, the NDTE System provides a continuous body armor plate surveillance capability as it collects data on inspected body armor plates such as lot number, cage code, contract number, serial number, national stock number (NSN) and radiographic images.
RS3-24-0039 | Follow-on: W56KGU-21-C-0030 CACI, INC. - FEDERAL | $25M-<$50 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Brian McGuire KS: Monique Bryant | Evaluation | Yes (KO) | Competitive Acquisition | Unrestricted | 2024-08-06 | 2025-05-02 | — | United States Army Futures Command, CCDC, C5ISR Center; Combat Capabilities Development Command (DEVCOM) Armaments Center; Research, Technology and Integration Directorate (RTI Directorate) | Network Exploitation Research and Development (NERD) | Contractor shall provide Research, Development, Test & Evaluation (RDT&E) support for Cyber Effects (CE) programs focusing on the maturation of Cyber and Electronic Warfare (EW) techniques and supporting technologies to defeat active and passive air/ground Intelligence Reconnaissance Surveillance (ISR) systems; terrestrial and beyond-line-of-sight communication systems; radar enabled kinetic weapon systems; and supporting processing systems.
RS3-24-0047 | Follow-on: GS00Q14OADU141, TO-W52P1J21F0209 LMI Consulting, LLC | Over $250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG DCOE (ACC-RI) Contracting Team | KO: Leslie Dickson KS: Darrin Hanson (P) and Steven Claeys (A) | Pre-Award/Package Development | Yes (MP) | Competitive Acquisition | Unrestricted | 2025-03-03 | 2025-06-02 | — | PEO EIS, PM ARDAP (Army Data and Analytics Platform) | Technical and Professional Advisory Services in support of PM ARDAP (Army Data and Analytics Platform) | Contractor shall provide professional SETA services with sufficient scientific background and business administration expertise to effectively support a full range of programmatic initiatives, inclusive of research, development, test and evaluation; budget and acquisition life-cycle support functions during all phases of planning, programming and execution; and the development/continued development, deployment and sustainment activities of PM ARDAP, its subordinate organizations and those organizations which have the managerial expertise to complement PM ARDAP's mission while meeting the Army’s IT goals and objectives.
RS3-24-0052 | New Requirement | $50M-<$100 Million | Three-year PoP, Base and Two Options | Internal Package - Division B | KO: John Harvey KS: Langston Guinn | Pre-Award/Package Development | Yes (KO) | TBD | TBD | TBD | TBD | — | PEO AVIATION | PM Uncrewed Aircraft Systems (UAS) Support | Contractor shall provide Engineering Services, Logistic Services, and Acquisition and Strategic Planning Services in support of the Uncrewed Aircraft Systems (UAS) managed by PM UAS. PM UAS supports a family of Small Uncrewed Aircraft Systems (SUAS) to include Future Tactical Uncrewed Aircraft Systems (FTUAS), Gray Eagle, One System Remote Video Terminal (OSRVT), Launched Effects (LE), and Uncrewed Vehicle Control (UVC). In addition, PM UASmanages initiatives ranging from new technological insertions to new UAS, legacy UAS and UAS sub-systems. PM UASanticipates the magnitude of work will be 40% Engineering Services, 30% Logistics Services, and 30% Acquisition and Strategic Planning Services over the life of the mission requirement.
RS3-24-0056 | New Requirement | $100M-<$250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG DCOE (ACC-RI) Contracting Team | KO: Jordan Cosgrove KS: Meghan Walsh | Solicitation | Yes (KO) | Competitive Acquisition | Unrestricted | End of Feb 2025 | TBD | — | PEO EIS, Enterprise Business Systems - Convergence (PM EBS-C) | PM EBS-C Technical Management and Advisory Support Services | In order to support the OTA effort and follow-on production effort, PM EBS-C is seeking technical management and advisory support services. Specifically, the Contractor shall develop and provide an organic capability to support a full range of required PM EBS-C services and all supporting directorates' services to include Business Process Reengineering (BPR), Enterprise Design and Information Technology (IT), Cloud Infrastructure, Cross Domain Solutions, Cybersecurity, Data Management, AI, UI/UX, Human Centered Design, Agile, Budget, Audit, Training, Fielding & Deployment, Systems Engineering, Solution Architecture, DevSecOps, Strategic Communications and General Program support. Additionally, Contractor shall provide program management, technical advisory, Subject Matter Expert (SME), consultation, and staff augmentation support services for non-governmental tasks that exceed organic capabilities in the areas of financial, logistical, technical, and business transformation and support required for the Enterprise Resource Planning (ERP) Systems, Legacy Systems, and related organizations' systems.
RS3-24-0059 | Follow-on: W15P7T-19-D-0181, TO-W56KGU20F0011 (RS3-19-0053) Parsons Government Services, Inc. | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Nick Martin KS: Ola Kaka | Evaluation | Yes (KO) | Competitive Acquisition | Unrestricted | 2024-12-20 | 2025-03-31 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR); Research, Technology & Integration Directorate (RTI) | Radar Division Program Management Support | Contractor shall provide the requisite operational, program management, technical, engineering, integration, prototype development and fabrication, program support services and products necessary for the C5ISR Center to meet its mission and customer needs. The services to be provided by the Contractor shall encompass a wide variety of program support for all elements of the acquisition cycle and the subsequent support of systems in the field. The Contractor shall also have the demonstrated resources to respond immediately to quick reaction requirements and situations.
RS3-24-0060 | Follow-on: W911S0-21-D-0006, TO-W911S024F0142 JANUS RESEARCH GROUP, LLC | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by MICC Fort Eustis Contracting Team | KO: Shaina McKeel KS: Ronald Pryor | Evaluation | Yes (KO) | Competitive Acquisition | Unrestricted | 2024-12-31 | 2025-05-21 | — | Army Futures and Concepts Center, Architecture Integration and Management Division (AIMD), Fort Eustis, VA | FCC AIMD Applications Support | AIMD is part of Army Futures Command (AFC), Futures and Concepts Center (FCC), Joint Base Langley-Eustis, VA. This task order provides support services to AIMD in the accomplishment of its mission and fulfillment of its role as the Army Futures Command’s Operational Architecture Executive Agent, and as system owner of the Army Capabilities and Architecture Development and Integration Environment (ArCADIE), Capability Development support services, and development and management of the FCC Forge system.
RS3-24-0062 | Follow-on: W15P7T-17-D-0139, TO-W56KGU20F0014 UNIVERSAL TECHNICAL RESOURCE SERVICES, INC. | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Anh Pena KS: Brianne Holmes | Pre-Award/Package Development | Yes (KO) | Competitive Acquisition | Restricted | TBD | 2025-06-30 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR) Center; Engineering & Systems Integration (ESI) Directorate | Defensive Cyber Solutions Branch (DCSB) Mission Support | Effort provides program management office support services and sustainment capabilities. These services require independent and objective oversight and ongoing evaluation of provisioned cybersecurity services provided to subscribers, alignment of new subscribers, invoicing of subscribers, monetary and budget tracking, management of products, processes and workforce, and the management of the assessment process.
RS3-24-0068 | New Requirement | $25M-<$50 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: Kyle Gorham KS: Daniela Miller | Evaluation | Yes (KO) | Competitive Acquisition | Restricted | 2025-02-21 | 2025-04-02 | — | Joint Warfare Analysis Center | Modeling and Simulation Support Services | The Joint Warfare Analysis Center (JWAC) provides the Combatant Commands (COCOMs), U.S. Strategic Command (USSTRATCOM) and the Joint Staff with effects-based, precision targeting options for selected networks and nodes in order to carry out the national security and military strategy of the United States during peace, crisis and war. JWAC maintains and enhances leading-edge technology and world-class subject matter expertise to provide the warfighter specialized engagement options against adversaries’ critical infrastructure and related systems. JWAC is located at the Naval Support Activity - South Potomac (NSA-SP) Base located in Dahlgren, Virginia (VA). Requirement Description: The contractor shall develop tools, models and simulations to enable the evaluation of disruption effects on adversary capabilities within specified scenario evaluation designs, experiment designs and computational analysis. The contractor shall also provide assistance in the application of methods to include the development and implementation of algorithms and mathematical methods in support of software capabilities.
RS3-24-0069 | Follow-on: W15P7T-19-D-0082, TO-W909MY23F0003 QinetiQ Inc. | $25M-<$50 Million | Four-year PoP, Base and Three Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Shanin Johnson KS: Bradley Lovett | Solicitation | Yes (KO) | Competitive Acquisition | Restricted | 2025-02-26 | 2025-05-01 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR); Research, Technology & Integration Directorate (RTI) | RTI Business and Operations Advanced Research and Development Support | Contractor shall provide technical and business coordination and operational support. Contractor shall also provide technology SMEs and program analysts to RTI. Specific tasks shall include technology trade-off analyses (providing insights on technologies that address capability needs, taking into consideration system size, weight and cost among other factors). In addition, technical reports and briefings, data items and insights on technical approaches shall be provided. Contractor shall have a broad range of technical expertise to analyze Army Sensor Technology needs and to evaluate trade-offs for sensor components, systems and architectures that could be leveraged to meet Army goals.
RS3-24-0070 | Follow-on: W15P7T-17-D-0125, TO-W15P7T21F0005 (RS3-19-0040) QED Systems, LLC | $25M-<$50 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division B (Branch C) Contracting Division | KO: Candace Hough KS: Tiffany Burke | Evaluation | Yes (KO) | Competitive Acquisition | Restricted | 2025-02-13 | 2025-08-19 | — | PEO C3N, PM Tactical Radios (TR), Product Manager Communications Security (PdM COMSEC) | PdM COMSEC Software Production and Post Deployment System Support | Contractor shall provide software engineering, software development, software maintenance, software upgrades, software testing, software integration, software training, technical management development and life cycle management support for legacy and new software in support of PdM COMSEC. The mission requirement also entails information and system security, network support to include analysis and operations, logistics and asset management support and system development.
RS3-24-0072 | Follow-on: W15P7T-19-D-0010, TO-W56KGU23F0013 (RS3-23-0009) SEMPER VALENS SOLUTIONS, INC | $100M-<$250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Nick Martin KS: Amy Pancio | Package Received | Yes (KO) | Competitive Acquisition | Restricted | TBD | 2025-09-15 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR) Center; Engineering & Systems Integration (ESI) Directorate | Engineering & Systems Integration Operations and Support 4 (ESI-OPS4) | Contractor shall provide the requisite program management, administrative support, property management, security, environmental and safety, technical support and facility support to include limited laboratory Sustainment, Renovation and Modernization (SRM) in accordance with Department of Army policy necessary for the Business and Operations (B&O) Portfolio to meet its mission and customer needs as directed by the C5ISR Center.
RS3-24-0074 | Follow-on: GS00Q14OADU125, TO- W91CRB-21-F-0434 NORTHROP GRUMMAN SYSTEMS CORPORATION | $100M-<$250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division D Contracting Division | KO: Shantice Wright KS: Sue Levush | Pre-Award/Package Development | Yes (KO) | Competitive Acquisition | Unrestricted | 2025-04-18 | 2025-07-01 | — | US Army Deputy Chief of Staff (DCS), Army G-8, Program Analysis and Evaluation (PA&E) Program Budget Data Management Division (PBDMD) | Planning, Programming, Budgeting, Business Operating System (PPBBOS-III) | Contractor shall support the management, development, maintenance and sustainment of the environment, systems and applications hosted in the ARC/cPROBE environment in support of Headquarters, Department of the Army. Contractor shall ensure all applications that are part of the ARC/cPROBE are operated and sustained in a cyber-secure manner. Contractor shall provide services for the business capability definition; architectural design and evaluation; prototyping; engineering development; configuration, integration and migration activities, along with maintenance and sustainment of all business applications and cloud infrastructure items. Each of these components shall be executed throughout the life of the contract/task order. • Component I: Cloud Infrastructure Activities • Component II: Security Activities • Component III: Maintenance and Sustainment Activities • Component IV: New Development of Systems/Applications • Component V: Enterprise Reporting • Component VI: Data Services • Component VII: Data Science Services
RS3-25-0002 | New Requirement | Under $25 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: John Harvey KS: Luis De La Cruz | Pre-Award/Package Development | Yes (KO) | TBD | TBD | TBD | TBD | — | Army National Guard (ARNG) | Program and Data Analytics Services | The Acquisition Program Management Office (APMO) and Joint Staff Resource Management Office (JS RMO) collect data relevant to requirements developed by the Army National Guard (ARNG) and National Guard Bureau (NGB) Joint Staff. This data is collected and then disseminated via reports to provide tracking of a requirement from start to finish. This allows ARNG leadership and JS leadership to assess cost, schedule, and performance across the various divisions. The ARNG G8 Data Analytics Group – Resourcing (DAG-R) provides the Chief Financial Officer (CFO) independent analytical capability. The DAG-R has three main goals: run the Planning, Programming and Budget Committee – Guard (PPBC-G) process and facilitate all supporting forums and activities; act as a clearinghouse for all analytics through an independent look at Planning, Programming, Budgeting and Execution (PPBE) resourcing actions and documents; and work with Army Resource Program Managers across the ARNG Directorate and the NGB Joint Staff to develop better tools and analytic techniques to improve efficacy of resource and funds management.
RS3-25-0009 | Follow-on: 47QRAD20D1042, TO-HC108423F0058 Credence Dynamo Solutions, LLC | Under $25 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division C Contracting Division | KO: Aaron Kazi KS: Rachel Polk | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2026-05-29 | — | PEO IEWS; PM PNT | PM PNT SETA Support | Contractor shall provide SETA support services to PM PNT. Please note. Additional mission requirement information will be provided once the requirement PWS is finalized.
RS3-25-0010 | Follow-on: W91CRB-20-C-0026 Sigmatech, Inc. | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG Division D Contracting Division | KO: Salma Williamson KS: David Lafferty | Package Received | Yes (KO) | TBD | TBD | TBD | 2025-09-15 | — | HQ, DA; ASA (ALT) | Consolidated Security Cooperation Requirements | The contractor shall provide all personnel, supervision and non-personal services necessary to perform project management and administrative expertise to support DASA DEC’s security cooperation activities.
RS3-25-0012 | Follow-on: W15P7T-17-D-0107/TO-W909MY19F0046; W909MY-12-D-0007/TO-0050; W909MY-12-D-0007/TO-0024; W15P7T-19-D-0038/TO-W909MY22F0086 BRTRC FEDERAL SOLUTIONS, INC. & FIBERTEK, INC. | Under $25 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG Division A Contracting Division | KO: Nina Bushnell KS: Asha Thomas | Pre-Award/Package Development | Yes (KO) | Competitive Acquisition | Unrestricted | 2025-04-02 | 2025-06-21 | — | United States Army Futures Command, CCDC, C5ISR Center; Combat Capabilities Development Command (DEVCOM) | Development, Engineering and Sustainment Support for the AutoDISE Software | Contractor shall support AutoDISE, a unique modeling and simulation software developed by the US Army, C5ISR Center RTI Power Division in support of Project Manager (PM) Expeditionary Energy and Sustainment Systems (E2S2). This software is used by the Armed Services and the Warfighter in the development, design and implementation of Multi-Domain Operations (MDO) Base Camps, Tactical Operation Centers (TOC), Base Camps (BC), Forward Operating Bases (FOB), Combat Outposts (COP) and Navy and Army Medical Field Hospitals (FH) and Hospital Centers (HC) in the areas of power, power distribution and environmental control system (heating and cooling). The AutoDISE software provides unique planning capabilities that enable planning, utilizing and integrating renewable energy, as well as, managing and assisting units in managing water and wastewater resources. As the US Military evolves and adapts to new challenges in an operational energy environment, AutoDISE software development and improvement must evolve to match operational requirements.
RS3-25-0013 | New Requirement | $25M-<$50 Million | Four-year PoP, 24-month Base and 24-month Option | External Package, being worked by ACC-APG, Division A Contracting Division | KO: TBD KS: TBD | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 1st QTR / FY 2026 | — | United States Army Futures Command, CCDC, C5ISR Center, DEVCOM; Research & Technology Integration Directorate (RTI), Modeling and Simulation Division (MSD) | Modeling, Simulation, Training, Integration and Concepts (MSTIC) Support | Contractor shall provide research, development, engineering, training, experimentation and systems integration support to the Research & Technology Integration Directorate (RTID), Modeling and Simulation Division (MSD) for internal efforts and external customer efforts reference MSD's mission to direct the development of state-of-the-art sensor models and simulation capabilities for end-to-end electronic sensor performance assessments to include support for Army decisions on current and advanced electronic sensor systems, single and fused sensor platforms and man-in-the-loop experimentation.
RS3-25-0014 | Follow-on: W15P7T-19-D-0157, TO-W56KGU20F0015 (RS3-19-0028) CACI Technologies, LLC. | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Brian McGuire KS: Brian Townsend | Pre-Award/Package Development | Yes (MP) | Competitive Acquisition | Unrestricted | 2025-03-31 | 2025-10-01 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR); Research, Technology & Integration Directorate (RTI) | Cross Domain Electronic Warfare & Survivability (CRODEWS) | Contractor shall provide engineering and programmatic support and assist in the design, development, integration, testing, documentation and evaluation for Cross Domain Electronic Warfare (EW) Survivability Capabilities.
RS3-25-0015 | Follow-on: PM TS SETA – W15P7T-17-D-0125, TO-W909MY23F0026; PM FPS – W15P7T-17-D-0125, TO-W909MY23F0071 (QED SYSTEMS LLC) PD Aerostats – W56KGY-18-C-0008 (NAVQSYS, LLC) PM BIO (PMOS) – GS00Q17GWD2266, TO-W909MY19F0068 (IPOWER LLC) PM BIO (PLEAC) – 47QRAA-18-D-00B9, TO-W909MY19F0073 (KIZANO CORP) PM GS – IAC MAC DTIC TO FA807518D0006, TO-FA807520F0037 (CACI, INC. - FEDERAL) | Over $250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG Ft Belvoir Contracting Division | KO: Rosetta Wisdom-Russell KS: Jada Carter | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2027-03-16 | — | PEO IEW&S; Project Manager Terrestrial Sensors (PM TS) | PM TS SETA Support Services | A singular consolidated Systems Engineering and Technical Assistance (SETA) Contract/Task Order to support Project Manager Terrestrial Sensors (PM TS) Headquarters and all PM TS subordinate product offices. Contractor shall provide SETA support services to include but not limited to budget, program analysis, General Funds Enterprise Business System (GFEBS) support, program management, engineering, cyber security, etc.
RS3-25-0016 | Follow-on: W15P7T-19-D-0038, TO-W909MY22F0086 (RS3-22-0026) Fibertek, Inc. | $25M-<$50 Million | Two-year PoP, Base and One Option | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Ashley Howard KS: Marvin Osselin | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2025-08-01 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR); Research, Technology & Integration Directorate (RTI) | Humanitarian Demining Research and Development (HD R&D) Program Support | The Humanitarian Demining Research and Development (HD R&D) Program requires various skill levels and expertise to support and execute strategic program plans. Specifically, skills in eight (8) major areas are required: (1) Testing HD R&D-developed systems at various test facilities located in the U.S. and OCONUS. (2) Developing and executing evaluation plans of HD R&D-developed systems in the context of live mine clearance operations in third world countries. These extended evaluations are referred to as Operational Field Evaluations (OFEs) and seek to provide value to the host Non-Governmental Organization (NGO) operators in terms of introduction of new and more efficient means of pursuing the many facets of Humanitarian Mine Action. (3) Maintaining this equipment while supporting various worldwide operational field evaluations at various test facilities located in the U.S. and OCONUS and in support of the OFEs. (4) Providing logistics support for OCONUS deployments of HD technologies to third world countries. (5) Support of the development, fabrication, demonstration and validation of equipment technologies developed by the HD R&D Program. (6) Preparing manuals, training guides and training videos in English and/or foreign languages to support the deployment of HD prototype technologies to host countries for operational field evaluations. (7) Maintaining and supporting the HD R&D Program website. (8) Participating in conferences, meetings, workshops or other events pertinent to the HD R&D program execution, including the demining requirements workshop conducted bi-annually and the Unexploded Ordnance (UXO) Working Group Meeting held bi-annually at OCONUS locations.
RS3-25-0017 | Follow-on: FA807518D0006/FA807522F0033 CACI, INC. – Federal | $50M-<$100 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: John Harvey KS: Nick Schafer | Pre-Award/Package Development | Yes (KO) | TBD | TBD | TBD | TBD | — | Army Futures Command; All-Domain Sensing (ADS) Cross-Functional Team (CFT) | Modernization Support for All-Domain Sensing | Contractor shall research, analyze and make recommendations in support of CFT advanced requirements. Support requirements include Multi-Sensor Dominance, Sensing Architecture, Advanced Processing and Dissemination of Information and Intelligence, Surveillance and Reconnaissance Data. Contractor shall provide interoperability system performance analysis, system integration analysis, technology enhancement capabilities recommendations, supportability engineering analysis, development and sustainment management analysis as well as technical assessments and analysis for program management.
RS3-25-0018 | Follow-on: W15P7T-19-D-0157, TO-W56KGU20F0015 (RS3-19-0028) EWSAGISE is the follow-on effort to CAGES. CACI Technologies, LLC. | $50M-<$100 Million | Four-year PoP, Base and Three Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Nick Martin KS: Maurice Hinkson | Package Received | Yes (KO) | Competitive Acquisition | Unrestricted | TBD | 2025-07-01 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR); Engineering & Systems Integration (ESI) Directorate | Electronic Warfare Survivability, Air/Ground, Integration, Systems Engineering (EWSAGISE) Support | Contractor shall provide engineering and programmatic support and assist in the design, development, integration, testing, documentation and evaluation of Multi Spectral EW Survivability Capabilities, Distributed Electronic Warfare, Low SWaP-C EW and Radar Sensors for Multi-mission Operations, Multi-function RF and EW Payloads, Counter C5ISR (C-C5ISR) Technology and Countermeasure (CM) Techniques.
RS3-25-0022 | Follow-on: FA880820D0002, TO-FA880724FB012 - A3M FA880820D0002, TO-FA880724FB011 - RAM L3 Technologies, Inc. | $100M-<$250 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division B; Branch A Contracting Division | KO: Mike Monticello KS: Alyson Scholz | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2027-03-29 | — | PEO C3T; PdM Satellite Communications | Air-Force Army Anti-Jam Modem (A3M) and Army Resilient Anti-Jam Modem (RAM) | Production and sustainment for the Air Force-Army Anti-Jam Modem (A3M) and the design and development of the Resilient Anti-jam Modem (RAM). Continue production and sustainment of the A3M and to procure production quantities and sustain the RAM. The Air Force and Army Anti-jam Modem (A3M) is an ACAT III program to develop, procure and field Protected Tactical Waveform (PTW) capable modems for tactical SATCOM operations. PTW capable modems are the user equipment enabling use of the Protected Anti-jam Tactical System (PATS). The PATS enterprise consists of the Protected Tactical Enterprise Service (PTES) enabling operations over existing Wideband Global Satellite (WGS) and the future Protected Tactical SATCOM (PTS) hub in space. The RAM Program will develop and procure operational PTW modems with an embedded ECU for integration with currently fielded, Military SATCOM (MILSATCOM) certified tactical terminals. The target terminals for the RAM Program include the Army PM-TN Suite of Terminals (SoTs), Scalable Network Node (SNN), SoTs Scalable Class of Unified Terminals (SCOUT), Point of Prescence (POP), Soldier Network Extension (SNE), Tactical Communications Node (TCN)-L Warfighter Information Network – Tactical (WIN-T). Please note. The Services may add additional terminals if other requirements arise. RAM Terminal Subsystem Enhancements are a particular implementation of the family of devices referred to as PATS modems. When RAM Terminal Subsystem Enhancements are integrated within an earth terminal, the combined system provides the capability of a PATS terminal and interoperability with the PATS family of systems.
RS3-25-0025 | Follow-on: W15P7T-17-D-0155, TO-W15P7T21F0110 (RS3-20-0003) AMENTUM SERVICES, INC. | $100M-<$250 Million | Five-year PoP, Base and Four Options | Internal Package - Division B | KO: Jeannette Brush KS: Kaitlyn Harward | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | TBD | — | Naval Air Systems Command (NAVAIR); Program Management Air (PMA) 263 Program Office | PMA 263 Small Unmanned Aircraft Systems (SUAS) Support | Contractor shall provide support deliverables for Group 1 and Group 2 SUAS and associated payloads through the application of knowledge and resources in achieving the requiring activity’s (RA's), Program Executive Office for Unmanned Aviation and Strike Weapons (PEO U&W), Small Tactical Unmanned Aircraft Systems (SUAS), Program Management Air (PMA) 263, Family of Small Unmanned Aircraft Systems (FoSUAS) Integrated Program Team (IPT) mission requirements. This effort will include logistics support, supply chain management, and engineering; Research, Development, Test and Evaluation (RDT&E); acquisition and strategic planning; and education and training for both Marine Corps and Navy units.
RS3-25-0026 | Follow-on: W15P7T-17-D-0122, TO-W909MY23F0032 (RS3-22-0042) Marton Technologies, Inc. | $25M-<$50 Million | Four-year PoP, Base and Three Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: TBD KS: TBD | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2025-09-21 | — | Command & Control, Communications, Computers, Cyber, Intelligence, Surveillance and Reconnaissance (C5ISR) Center; Research, Technology & Integration Directorate (RTI) | RTI Facilities, Logistics, Environmental, Equipment and Testing (FLEET) Support | The Command, Control, Communications, Computers, Cyber, Intelligence, Surveillance, and Reconnaissance (C5ISR) Center, Research & Technology Integration Directorate (RTI) has the mission to provide operational support in the augmentation, development, maintenance, and refurbishment of sensor laboratories and sensor testing and evaluation sites residing within the secured Area 300 Compound; Fort Belvoir, VA; Davison Airfield, VA; Fort Walker, VA; and Aberdeen Proving Ground, MD. The contractor shall provide support in the areas of equipment management, maintenance and property control, transportation, warehouse receiving/distribution, industrial hygiene and environmental safety protocol, and electro-optic/infrared (EO/IR) and other sensor technology testing and evaluation support. Contractor support performed under this effort will be within the regulations and guidance defined by Department of Defense (DoD), Department of Army, AFC, DEVCOM and the C5ISR Center. The contractor shall also provide the necessary personnel to support the augmentation, development, maintenance, and refurbishment of sensor laboratories and sensor testing and evaluation sites residing within the secured Area 300 Compound; Fort Belvoir, VA; Davison Airfield, VA; Fort Walker, VA; and Aberdeen Proving Ground, MD. RTI Directorate’s research and development facilities are located within multiple restricted areas housing several laboratory facilities with unique requirements to include chemical labs, laser labs, laser ranges, a semi-conductor microfactory, and an indoor firing range. The laboratories and testing facilities must remain fully operational 365 days a year.
RS3-25-0029 | New Requirement | $25M-<$50 Million | Three-year PoP, Base and Two Options | External Package, being worked by ACC-NJ Contracting Division | KO: Charlotte Sylvain KS: Howard Kane | Pre-Award/Package Development | Yes (MP) | TBD | TBD | 2025-03-31 | 2025-06-18 | — | DEVCOM- Armaments Center | DEVCOM AC HQ Operational Support | Contractor shall provide expert operations and technical services in support of efforts within the U.S. Army Combat Capabilities Development Command – Armaments Center (DEVCOM-AC) Headquarters and its subordinate directorates. Contractor shall provide the requisite program management, administrative, facility management, logistics, property management, security, software engineering support, systems administration support and technical support necessary for DEVCOM-AC Headquarters and its subordinate directorates to meet its mission and customer needs. Contractor shall provide a broad range of operational and administrative support functions and participate in program planning, monitoring, scheduling and control of operation support for the DEVCOM-AC systems-of-systems, family-of-systems, platforms, systems, operations of facilities and infrastructure. Contractor shall also provide various Systems Engineering and Technical Assistance (SETA) services in support of DEVCOM-AC.
RS3-25-0030 | New Requirement | $25M-<$50 Million | Four-year PoP, Base and Three Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: Megan Francis KS: Shanin Johnson | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2025-09-30 | — | United States Army Futures Command, CCDC (DEVCOM), C5ISR Center; Ground Combat Systems Division (GCSD), Research and Technology Integration Directorate (RTI) | Strategic Monitoring and Autonomous Response Technologies (SMART) | Contractor shall conduct expeditious and thorough research, development, engineering, prototyping, integration, demonstration and project management to execute autonomous manned vehicle and dismounted soldier sensor technology projects. Contractor shall provide technical, logistical and program management support required to assist each technology area in the investigation, development, integration, maturation and the demonstration of relevant technology projects integrated on manned, unmanned, optionally manned, aerial and dismounted soldier demonstration platforms. The Strategic Monitoring and Autonomous Response Technologies (SMART) Program requires development, engineering and management support for advanced sensor technologies/systems and autonomous system integration across dismounted Soldiers, manned and unmanned ground vehicles and small unmanned aerial systems. Contractor shall provide trade studies, market surveys, component research, software and hardware development and integration, system development, engineering analysis, modeling, system integration and testing. Please note. The sensor and autonomous technologies require a high level of specialized technical and management capability to support the advancement of sensor technologies and autonomous systems to improve Soldier effectiveness while reducing cognitive load, improving decision-making timelines and increasing lethality in complex operational environments against conventional and unconventional threats.
RS3-25-0031 | Follow-on: W31P4Q-23-F-0291; W31P4Q-24-F-0012; W31P4Q-24-F-0024; W31P4Q-24-F-0055 Northrop Grumman Systems Corporation | $25M-<$50 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-Redstone Arsenal (ACC-RSA) Contracting Division | KO: Susan E. Ruzicka KS: Melissa Rios Thomas | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2025-04-25 | — | HQ, PEO MS | Air and Missile Defense Planning and Control System (AMDPCS) Tactical Support | Air and Missile Defense Planning and Control System (AMDPCS) Tactical Support (ATS) Contract for hardware and software products providing Engagement Operations and Force Operations capabilities for Air and Missile Defense (AMD) units. Contractor shall build new and update integrated product support (IPS) products for the FAAD Sensor Node and Air Defense Airspace Management (ADAM) System resulting from the Handheld, Manpack and Small Form Fit (HMS) Radio ECP, Common Data Link Interface Module (CDLIM) ECP and Assured Positioning, Navigation, and Timing (APNT) ECP. Updates shall include Government approved changes generated from DA Form 2028s, changes in hardware, changes from information provided by the Government and changes recommended by the contractor. In addition, the contractor shall provide technical support/expertise to perform system field level engineering, technical, maintenance, cybersecurity, logistics and training support for fielded AMDPCS. Contractor shall also provide and/or be responsible for product support analysis, maintenance planning, provisioning, technical manuals, modification work orders (MWO), service contract reporting, program management, engineering services, data management, quality assurance and cybersecurity compliance.
RS3-25-0032 | New Requirement | $25M-<$50 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division A Contracting Division | KO: TBD KS: TBD | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | October/ November 2025 | — | United States Army Futures Command, CCDC, C5ISR Center, Combat Capabilities Development Command (DEVCOM), Research and Technology Integration Directorate (RTI), Integrated Offensive Electronic Warfare (IOEW) Branch | Non-Kinetic Effects (NoKE) Mission Requirement | The U.S. Army Combat Capabilities Development Command (DEVCOM), Command, Control, Computers, Communications, Cyber, Intelligence, Surveillance and Reconnaissance Center (C5ISR), Research and Technology Integration Directorate (RTI), Integrated Offensive Electronic Warfare (IOEW) Branch has a requirement for Program Management; Purchasing; Subject Matter Expertise (SME); Hardware and Software Design and Development; Air and Ground Electromagnetic Warfare Engineering Support, Modeling and Simulation; Electromagnetic Warfare Software and Firmware Development/Implementation, Lab Experiments, Field Demonstration, Engineering Requirements and Concept of Operations Analysis; and other urgent time-critical requirements. The contractor shall develop advanced Electromagnetic Warfare (EW) systems that can effectively counter and disrupt sophisticated adversary systems including communication, radar and surveillance capabilities to achieve spectrum dominance in multi-domain operations. The focus is on maturing Cyber and Electronic Warfare techniques and supporting technologies to defeat various threats to include Intelligence, Surveillance, and Reconnaissance (ISR) Systems; Communication Systems; Radar-enabled Kinetic Weapon Systems and Supporting Processing Systems. The contractor shall provide the Warfighter with advanced EW capabilities that can counter existing and emerging threats, support a wide range of military operations, achieve spectrum dominance, improve kinetic weapon effectiveness and provide enemy situation awareness, targeting and non-kinetic effects. Research and development efforts may focus on advanced signal processing techniques, electronic attack capabilities, cyber warfare techniques, spectrum sensing and management and artificial intelligence and machine learning.
RS3-25-0033 | Follow-on: GS00Q14OADS437, TO-W911QX21F0162 SURVICE Engineering Company, LLC | $25M-<$50 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-Adelphi Contracting Division | KO: Meghan Whitmore KS: Deneise Jackson Acquisition Specialist: Karen Millner | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2025-05-23 | — | United States Army Futures Command, CCDC, C5ISR Center; United States Army Combat Capabilities Development Command (DEVCOM) Analysis Center (DAC) | DEVCOM DAC Data Analysis Mission Requirement | The United States Army Combat Capabilities Development Command (DEVCOM) Analysis Center (DAC) requires technical support across its broad mission to deliver objective analysis, experimentation and data to ensure readiness today and a more lethal future force tomorrow. The DAC specifically requires technical expertise in data, experimentation and analysis across ballistic, chemical, biological, radiological and nuclear (CBRN) defense, and electronic and cyber warfare. The Contractor shall research and develop innovative ways using state-of- the-art methods and software platforms to support the DAC mission of performing data analysis to inform decisions in support of the Army’s Future Force Modernization Enterprise (FFME) and the Joint Services. The DAC is tasked by other Army and Joint Agency/Activities to perform a range of data analysis to evaluate evolving technologies and capabilities in support of the Warfighter. Specifically: 1) Developing interactive visualization to more effectively communicate Survivability/Lethality/Vulnerability (SLV) Analysis 2) Instrumentation and measurement techniques for data generation or modeling verification, 3) Performing CBRN defense system performance analysis, and 4) Technical program data and process management.
RS3-25-0034 | Follow-on: W15P7T-19-D-0206, TO-W56KGY22F0028 (RS3-21-0007) Envision Innovative Solutions, Inc. | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division C Contracting Division | KO: Lawrence Holton KS: Cuong Luu | Market Research Initiative | Yes (MP) | TBD | TBD | TBD | 2026-10-01 | — | PEO IEWS; PEO IEW&S Headquarters | Program Executive Office, Intelligence, Electronic Warfare and Sensors (PEO IEW&S) Systems Engineering and Technical Assistance Support (SETA) Task Order for IEW&S Headquarters (HQ) | Contractor shall provide technical, engineering, acquisition, program management, operational, security, logistics, administrative, financial, contract planning and business support services in support of PEO IEW&S and its mission requirements to include but not limited to Program of Record (POR) and Quick Reaction Capability (QRC) Systems.
RS3-25-0035 | Follow-on: W15P7T-19-D-0131, TO-W56KGY21F0025 (RS3-18-0081) TELESIS CORPORATION | $50M-<$100 Million | Five-year PoP, Base and Four Options | External Package, being worked by ACC-APG, Division C Contracting Division | KO: Megan Farley KS: Christopher Laird | Pre-Award/Package Development | Yes (MP) | TBD | TBD | TBD | 2026-11-02 | — | PEO IEWS; Product Manager (PdM) Multi-Mission Surveillance Systems (PdM M2S2) | PdM M2S2 SETA | Product Manager (PdM) Multi-Mission Surveillance Systems’ (M2S2) portfolio of systems consists of the AN/TPQ-50 Lightweight Counter Mortar Radar (LCMR), the AN/TPQ-53 Counterfire Target Acquisition Radar (CTAR), FIREFINDER Family of Systems (e.g. AN/TPQ-36/37) and related Foreign Military Sales (FMS) radar systems. Contractor shall provide services to support PdM M2S2 in the following areas: programmatic, technical, engineering, testing, logistics, maintenance, training, integration, business management, administrative and operational program support. Services shall assist PdM M2S2 in the successful product development, acquisition, sustainment, supportability, fabrication, overhaul, fielding, training, de-fielding and administration. Primary location of work performance will be Aberdeen Proving Ground (APG), MD and additional Continental United States (CONUS) locations to include but not limited to Syracuse, NY and Yuma Proving Ground (YPG), AZ. Work performance locations outside CONUS may include Kuwait, Iraq, Afghanistan, Republic of Korea, NATO and European countries as well as other facility locations as required.