## Cover
Domestic Private Sector Workload Estimate
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
CMAV Workload FY25 Q2 – FY26 Q1 as of 05 FEBRUARY 2025
Industry Version
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## Notes
Data contained in this report reflects the Navy program of record as of 05 FEBRUARY 2025.
This report is provided to our CONUS industry partners for information and planning purposes only. The information provided reflects a broad overview of current maintenance schedules and is subject to change based on operational commitments. It does not constitute a request for information or proposals, nor is it a commitment to contract work in accordance with this plan.
The next bi-monthly CMAV workload projections are targeted for release no later than 30 APRIL 2025.
Availability duration and schedule review, tailored acquisition strategies and ongoing budget negotiations may refine out-year projections.
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## MARMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2023-11-20 | 2025-03-31 | 498
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2024-11-12 | 2025-01-10 | 60
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-10 | 40
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-31 | 61
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2024-12-02 | 2025-02-09 | 70
LSD 51 | OAK HILL | Little Creek | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-31 | 54
DDG 98 | FORREST SHERMAN | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-24 | 47
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-02-07 | 61
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-03-07 | 89
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2024-12-16 | 2025-03-21 | 96
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 96 | BAINBRIDGE | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-31 | 47
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-02-07 | 54
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 57 | MITSCHER | Norfolk | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2025-01-27 | 2025-03-07 | 40
DDG 103 | TRUXTUN | Norfolk | CMAV (A) | ACTIVE | 2025-02-17 | 2025-03-14 | 26
DDG 67 | COLE | Norfolk | CMAV (A) | ACTIVE | 2025-02-18 | 2025-04-04 | 46
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-21 | 26
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2025-03-10 | 2025-04-11 | 33
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2025-03-31 | 2025-09-26 | 180
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2025-03-31 | 2025-05-04 | 35
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2025-04-07 | 2025-04-25 | 19
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2025-04-07 | 2025-05-09 | 33
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
DDG 96 | BAINBRIDGE | Norfolk | CMAV (A) | ACTIVE | 2025-04-21 | 2025-05-09 | 19
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2025-04-21 | 2025-05-30 | 40
DDG 57 | MITSCHER | Norfolk | CMAV (A) | ACTIVE | 2025-04-21 | 2025-06-06 | 47
DDG 96 | BAINBRIDGE | Norfolk | CMAV (A) | ACTIVE | 2025-05-19 | 2025-06-20 | 33
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2025-05-19 | 2025-09-25 | 130
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2025-05-27 | 2025-09-25 | 122
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2025-06-02 | 2025-06-27 | 26
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2025-06-02 | 2025-07-11 | 40
LSD 51 | OAK HILL | Little Creek | CMAV (A) | ACTIVE | 2025-07-14 | 2025-08-24 | 42
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2025-07-14 | 2025-09-19 | 68
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2025-07-15 | 2025-08-12 | 29
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2025-07-15 | 2025-08-12 | 29
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2025-07-15 | 2025-08-12 | 29
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-29 | 40
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-29 | 40
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-29 | 40
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-31 | 42
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2025-07-28 | 2025-08-22 | 26
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2025-08-04 | 2025-09-12 | 40
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2025-08-04 | 2025-09-12 | 40
DDG 67 | COLE | Norfolk | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-28 | 49
DDG 103 | TRUXTUN | Norfolk | CMAV (A) | ACTIVE | 2025-10-20 | 2025-11-28 | 40
LSD 50 | CARTER HALL | Little Creek | CMAV (A) | ACTIVE | 2025-10-27 | 2026-01-09 | 75
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2025-11-17 | 2026-01-09 | 54
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2025-11-24 | 2026-01-16 | 54
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2025-12-01 | 2026-01-23 | 54
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2025-12-01 | 2026-01-23 | 54
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2025-12-15 | 2026-02-06 | 54
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SERMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2024-02-05 | 2025-04-30 | 451
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2024-08-05 | 2025-02-07 | 187
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2024-10-14 | 2025-02-21 | 131
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-10 | 54
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-10 | 40
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-31 | 61
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-31 | 47
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2025-02-18 | 2025-03-14 | 25
LCS 29 | BELOIT | Mayport | CMAV (A) | ACTIVE | 2025-02-24 | 2025-04-25 | 61
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2025-03-03 | 2025-03-21 | 19
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2025-03-03 | 2025-04-11 | 40
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2025-03-03 | 2025-05-09 | 68
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2025-03-03 | 2026-01-02 | 306
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2025-03-07 | 2025-10-17 | 225
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2025-03-24 | 2025-04-11 | 19
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2025-04-07 | 2025-04-25 | 19
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2025-04-28 | 2025-05-30 | 33
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2025-04-28 | 2025-06-20 | 54
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2025-05-05 | 2025-07-25 | 82
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2025-05-12 | 2025-06-13 | 33
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2025-05-12 | 2025-06-20 | 40
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2025-06-09 | 2025-07-11 | 33
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2025-06-09 | 2025-10-06 | 120
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2025-06-23 | 2025-08-01 | 40
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2025-07-07 | 2025-08-15 | 40
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2025-07-07 | 2025-08-15 | 40
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2025-07-07 | 2025-08-15 | 40
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2025-08-04 | 2025-08-29 | 26
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2025-08-04 | 2025-09-12 | 40
LCS 27 | NANTUCKET | Mayport | CMAV (A) | ACTIVE | 2025-08-04 | 2025-10-31 | 89
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2025-08-18 | 2025-09-28 | 42
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2025-09-02 | 2025-10-10 | 39
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2025-10-20 | 2025-11-21 | 33
LCS 29 | BELOIT | Mayport | CMAV (A) | ACTIVE | 2025-10-20 | 2026-02-01 | 105
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2025-10-27 | 2025-12-05 | 40
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2025-11-10 | 2025-12-07 | 28
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2025-11-24 | 2025-12-26 | 33
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2025-11-24 | 2026-01-02 | 40
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2025-12-01 | 2026-01-09 | 40
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2025-12-15 | 2026-01-23 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SWRMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2024-08-19 | 2025-01-05 | 140
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-17 | 61
LSD 42 | GERMANTOWN | San Diego | CMAV (A) | ACTIVE | 2024-11-18 | 2025-02-25 | 100
LCS 30 | CANBERRA | San Diego | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-07 | 44
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-10 | 40
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-17 | 47
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-17 | 47
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2024-12-05 | 2025-01-05 | 32
LCS 16 | TULSA | San Diego | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2024-12-09 | 2025-02-28 | 82
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2024-12-13 | 2025-02-07 | 57
LCS 32 | SANTA BARBARA | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-17 | 33
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-02-11 | 58
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2024-12-30 | 2025-02-14 | 47
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2025-01-02 | 2025-02-14 | 44
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
LSD 49 | HARPERS FERRY | San Diego | CMAV (A) | ACTIVE | 2025-01-08 | 2025-02-14 | 38
LPD 25 | SOMERSET | San Diego | CMAV (A) | ACTIVE | 2025-01-13 | 2025-02-21 | 40
LSD 52 | PEARL HARBOR | San Diego | CMAV (A) | ACTIVE | 2025-01-13 | 2025-03-10 | 57
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2025-01-20 | 2025-02-28 | 40
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2025-01-21 | 2025-02-21 | 32
CG 70 | LAKE ERIE | San Diego | CMAV (A) | ACTIVE | 2025-01-31 | 2025-03-13 | 42
LHA 7 | TRIPOLI | San Diego | CMAV (A) | ACTIVE | 2025-02-03 | 2025-04-18 | 75
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2025-02-17 | 2025-05-16 | 89
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2025-02-18 | 2025-03-28 | 39
LHD 2 | ESSEX | San Diego | CMAV (A) | ACTIVE | 2025-02-20 | 2025-04-01 | 41
LCS 10 | GABRIELLE GIFFORDS | San Diego | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-21 | 26
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2025-02-24 | 2025-04-04 | 40
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2025-03-01 | 2025-03-20 | 20
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2025-03-10 | 2025-03-30 | 21
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2025-03-10 | 2025-04-18 | 40
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2025-03-10 | 2025-05-02 | 54
LPD 27 | PORTLAND | San Diego | CMAV (A) | ACTIVE | 2025-03-14 | 2025-05-09 | 57
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2025-03-24 | 2025-04-13 | 21
LPD 26 | JOHN P MURTHA | San Diego | CMAV (A) | ACTIVE | 2025-03-26 | 2025-05-09 | 45
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2025-04-07 | 2025-07-18 | 103
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-23 | 40
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-23 | 40
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-23 | 40
DDG 63 | STETHEM | San Diego | CMAV (A) | ACTIVE | 2025-04-21 | 2025-06-13 | 54
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2025-04-28 | 2025-06-05 | 39
LHD 8 | MAKIN ISLAND | San Diego | CMAV (A) | ACTIVE | 2025-05-05 | 2025-07-02 | 59
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2025-05-09 | 2025-06-13 | 36
CG 65 | CHOSIN | San Diego | CMAV (A) | ACTIVE | 2025-05-12 | 2025-06-22 | 42
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2025-05-19 | 2025-06-27 | 40
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2025-05-19 | 2025-06-27 | 40
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2025-05-19 | 2025-07-11 | 54
LCS 36 | KINGSVILLE | San Diego | CMAV (A) | ACTIVE | 2025-05-26 | 2025-06-30 | 36
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2025-06-02 | 2025-07-11 | 40
LHD 2 | ESSEX | San Diego | CMAV (A) | ACTIVE | 2025-06-09 | 2025-07-18 | 40
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2025-06-09 | 2025-07-18 | 40
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2025-06-16 | 2025-07-18 | 33
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2025-06-16 | 2025-07-30 | 45
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2025-06-17 | 2025-07-25 | 39
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2025-06-30 | 2025-07-20 | 21
LSD 49 | HARPERS FERRY | San Diego | CMAV (A) | ACTIVE | 2025-07-07 | 2025-07-27 | 21
LCS 12 | OMAHA | San Diego | CMAV (A) | ACTIVE | 2025-07-14 | 2025-07-31 | 18
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2025-07-14 | 2025-09-05 | 54
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-29 | 40
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-19 | 40
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2025-08-18 | 2025-09-26 | 40
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2025-08-29 | 2025-10-03 | 36
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2025-09-01 | 2025-10-03 | 33
LCS 36 | KINGSVILLE | San Diego | CMAV (A) | ACTIVE | 2025-09-04 | 2025-09-30 | 27
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2025-09-08 | 2025-10-17 | 40
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2025-09-08 | 2025-10-31 | 54
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2025-09-11 | 2025-10-24 | 44
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2025-09-15 | 2025-10-17 | 33
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2025-09-15 | 2025-10-17 | 33
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2025-09-15 | 2025-10-24 | 40
LCS 28 | SAVANNAH | San Diego | CMAV (A) | ACTIVE | 2025-10-06 | 2025-10-31 | 26
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2025-10-06 | 2025-11-14 | 40
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2025-10-06 | 2025-11-14 | 40
DDG 93 | CHUNG-HOON | San Diego | CMAV (A) | ACTIVE | 2025-10-20 | 2025-11-14 | 26
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2025-10-20 | 2025-11-28 | 40
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2025-10-20 | 2025-11-28 | 40
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2025-10-27 | 2025-11-21 | 26
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2025-11-03 | 2025-11-21 | 19
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2025-11-03 | 2026-01-09 | 68
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2025-11-06 | 2025-12-19 | 44
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2025-11-17 | 2026-01-02 | 47
LCS 26 | MOBILE | San Diego | CMAV (A) | ACTIVE | 2025-11-21 | 2026-01-09 | 50
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2025-11-24 | 2026-01-09 | 47
DDG 63 | STETHEM | San Diego | CMAV (A) | ACTIVE | 2025-11-24 | 2026-01-09 | 47
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2025-11-25 | 2026-01-09 | 46
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2025-12-12 | 2026-01-25 | 45
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2025-12-15 | 2026-01-23 | 40
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2025-12-22 | 2026-01-30 | 40
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2025-12-22 | 2026-02-17 | 58
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## NWRMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2024-10-21 | 2025-01-03 | 75
DDG 100 | KIDD | Everett | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-05 | 42
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2025-01-06 | 2025-01-31 | 26
DDG 102 | SAMPSON | Everett | CMAV (A) | ACTIVE | 2025-02-19 | 2025-03-18 | 28
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2025-02-21 | 2025-03-19 | 27
CG 71 | CAPE ST GEORGE | Everett | CMAV (A) | ACTIVE | 2025-03-12 | 2025-06-03 | 84
DDG 53 | JOHN PAUL JONES | Everett | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-29 | 46
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2025-11-17 | 2025-12-26 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## HRMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2024-11-12 | 2025-01-05 | 55
CG 67 | SHILOH | Pearl Harbor | CMAV (A) | ACTIVE | 2024-12-09 | 2025-02-08 | 62
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2025-01-06 | 2025-03-03 | 57
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2025-02-03 | 2025-03-28 | 54
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-14 | 19
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2025-03-17 | 2025-04-18 | 33
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2025-05-05 | 2025-06-27 | 54
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2025-05-26 | 2025-06-27 | 33
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2025-06-09 | 2025-07-18 | 40
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2025-06-30 | 2025-08-08 | 40
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-05 | 26
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-19 | 40
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2025-09-23 | 2025-11-13 | 52
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2025-09-29 | 2025-11-07 | 40
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2025-10-20 | 2025-11-09 | 21
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2025-11-12 | 2025-12-19 | 38
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2025-11-24 | 2025-12-30 | 37
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”