## Cover
Domestic Private Sector Workload Estimate
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
CMAV Workload FY24 Q2 – FY25 Q1 as of 31 JANUARY 2024
Industry Version
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## Notes
Data contained in this report reflects the Navy program of record as of 31 JANUARY 2023.
This report is provided to our CONUS industry partners for information and planning purposes only. The information provided reflects a broad overview of current maintenance schedules and is subject to change based on operational commitments. It does not constitute a request for information or proposals, nor is it a commitment to contract work in accordance with this plan.
The next bi-monthly CMAV workload projections are targeted for release no later than 30 APRIL 2024.
Availability duration and schedule review, tailored acquisition strategies and ongoing budget negotiations may refine out-year projections.
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## MARMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2024-01-03 | 2024-03-08 | 66
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2024-01-16 | 2024-03-15 | 60
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2024-01-22 | 2024-02-16 | 26
DDG 67 | COLE | Norfolk | CMAV (A) | ACTIVE | 2024-02-05 | 2024-03-01 | 26
DDG 57 | MITSCHER | Norfolk | CMAV (A) | ACTIVE | 2024-02-05 | 2024-03-29 | 54
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2024-02-12 | 2024-04-29 | 78
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2024-02-12 | 2024-03-22 | 40
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2024-02-26 | 2024-03-29 | 33
CG 69 | VICKSBURG | Norfolk | CMAV (A) | ACTIVE | 2024-03-04 | 2024-06-28 | 117
LHD 5 | BATAAN | Norfolk | CMAV (A) | ACTIVE | 2024-03-25 | 2024-04-26 | 33
LPD 19 | MESA VERDE | Norfolk | CMAV (A) | ACTIVE | 2024-03-25 | 2024-05-05 | 42
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2024-03-25 | 2024-04-19 | 26
DDG 61 | RAMAGE | Norfolk | CMAV (A) | ACTIVE | 2024-04-08 | 2024-05-19 | 42
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2024-04-15 | 2024-05-24 | 40
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2024-05-06 | 2024-07-05 | 61
DDG 79 | OSCAR AUSTIN | Norfolk | CMAV (A) | ACTIVE | 2024-05-06 | 2024-06-14 | 40
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2024-05-20 | 2024-08-09 | 82
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2024-05-20 | 2024-06-28 | 40
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2024-05-20 | 2024-06-21 | 33
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2024-05-20 | 2024-07-12 | 54
CG 55 | LEYTE GULF | Norfolk | CMAV (A) | ACTIVE | 2024-05-28 | 2024-09-26 | 122
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2024-05-28 | 2024-08-09 | 74
LHD 5 | BATAAN | Norfolk | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-07 | 35
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-12 | 40
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2024-06-10 | 2024-07-19 | 40
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2024-07-08 | 2024-07-26 | 19
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2024-07-08 | 2024-08-02 | 26
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2024-07-08 | 2024-08-16 | 40
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-20 | 33
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-27 | 40
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-27 | 40
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-27 | 40
DDG 96 | BAINBRIDGE | Norfolk | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-04 | 40
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-04 | 40
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2024-09-09 | 2024-09-27 | 19
DDG 79 | OSCAR AUSTIN | Norfolk | CMAV (A) | ACTIVE | 2024-10-21 | 2024-11-29 | 40
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2024-10-21 | 2024-11-15 | 26
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2024-10-28 | 2024-12-06 | 40
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-10 | 54
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-10 | 54
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-03 | 40
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-10 | 47
LSD 51 | OAK HILL | Little Creek | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-31 | 54
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-02-14 | 68
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2024-12-16 | 2025-02-21 | 68
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-02-02 | 49
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2024-12-30 | 2025-02-09 | 42
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SERMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2024-01-02 | 2024-02-09 | 39
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2024-01-04 | 2024-02-23 | 51
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2024-02-05 | 2024-06-14 | 131
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2024-02-05 | 2024-03-01 | 26
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2024-02-05 | 2024-03-08 | 33
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2024-02-05 | 2024-03-10 | 35
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2024-02-20 | 2024-04-12 | 53
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2024-02-26 | 2024-04-25 | 60
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2024-03-11 | 2024-03-29 | 19
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2024-03-18 | 2024-04-14 | 28
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2024-04-22 | 2024-06-21 | 61
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2024-04-29 | 2024-06-07 | 40
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2024-05-13 | 2024-06-21 | 40
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2024-05-20 | 2024-06-21 | 33
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2024-05-28 | 2024-07-12 | 46
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2024-05-28 | 2024-07-05 | 39
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-12 | 40
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-12 | 40
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2024-07-15 | 2024-08-25 | 42
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2024-08-12 | 2024-09-20 | 40
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2024-08-12 | 2024-11-15 | 96
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-13 | 26
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2024-08-19 | 2024-10-04 | 47
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-27 | 40
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2024-10-07 | 2024-11-15 | 40
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2024-10-15 | 2024-11-08 | 25
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-10 | 54
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-10 | 54
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-10 | 47
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SWRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2024-01-02 | 2024-02-13 | 43
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2024-01-08 | 2024-03-15 | 68
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2024-01-08 | 2024-07-17 | 192
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2024-01-08 | 2024-02-16 | 40
LCS 32 | SANTA BARBARA | San Diego | CMAV (A) | ACTIVE | 2024-01-08 | 2024-03-15 | 68
DDG 93 | CHUNG-HOON | San Diego | CMAV (A) | ACTIVE | 2024-01-16 | 2024-02-02 | 18
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2024-01-20 | 2024-03-15 | 56
LSD 49 | HARPERS FERRY | San Diego | CMAV (A) | ACTIVE | 2024-01-29 | 2024-03-01 | 33
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2024-02-05 | 2024-04-26 | 82
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2024-02-17 | 2024-03-17 | 30
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2024-02-19 | 2024-03-29 | 40
DDG 1001 | MICHAEL MONSOOR | San Diego | CMAV (A) | ACTIVE | 2024-02-20 | 2024-03-29 | 39
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2024-02-20 | 2024-03-18 | 28
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2024-02-26 | 2024-04-05 | 40
LSD 52 | PEARL HARBOR | San Diego | CMAV (A) | ACTIVE | 2024-03-04 | 2024-04-26 | 54
DDG 92 | MOMSEN | San Diego | CMAV (A) | ACTIVE | 2024-03-11 | 2024-03-29 | 19
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2024-03-11 | 2024-04-19 | 40
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2024-03-18 | 2024-05-17 | 61
DDG 63 | STETHEM | San Diego | CMAV (A) | ACTIVE | 2024-03-18 | 2024-04-07 | 21
LHA 7 | TRIPOLI | San Diego | CMAV (A) | ACTIVE | 2024-03-18 | 2024-04-26 | 40
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2024-03-25 | 2024-05-03 | 40
LPD 22 | SAN DIEGO | San Diego | CMAV (A) | ACTIVE | 2024-03-25 | 2024-07-12 | 110
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2024-03-28 | 2024-05-09 | 43
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2024-04-01 | 2024-05-10 | 40
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2024-04-08 | 2024-05-03 | 26
LCS 30 | CANBERRA | San Diego | CMAV (A) | ACTIVE | 2024-04-15 | 2024-05-24 | 40
LSD 42 | GERMANTOWN | San Diego | CMAV (A) | ACTIVE | 2024-04-15 | 2024-07-05 | 82
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2024-04-15 | 2024-05-24 | 40
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2024-05-13 | 2024-05-31 | 19
LCS 12 | OMAHA | San Diego | CMAV (A) | ACTIVE | 2024-05-27 | 2024-07-05 | 40
LCS 28 | SAVANNAH | San Diego | CMAV (A) | ACTIVE | 2024-05-28 | 2024-07-05 | 39
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-17 | 45
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-12 | 40
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2024-06-11 | 2024-07-05 | 25
DDG 88 | PREBLE | San Diego | CMAV (A) | ACTIVE | 2024-06-12 | 2024-07-25 | 44
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2024-06-20 | 2024-07-19 | 30
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2024-06-24 | 2024-08-02 | 40
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2024-07-01 | 2024-08-09 | 40
DDG 1001 | MICHAEL MONSOOR | San Diego | CMAV (A) | ACTIVE | 2024-07-01 | 2024-08-23 | 54
LCS 16 | TULSA | San Diego | CMAV (A) | ACTIVE | 2024-07-01 | 2024-08-09 | 40
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2024-07-15 | 2024-08-23 | 40
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2024-07-29 | 2024-09-09 | 43
LPD 27 | PORTLAND | San Diego | CMAV (A) | ACTIVE | 2024-07-29 | 2024-09-06 | 40
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2024-08-05 | 2024-09-13 | 40
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2024-08-05 | 2024-09-13 | 40
LHA 7 | TRIPOLI | San Diego | CMAV (A) | ACTIVE | 2024-08-05 | 2024-09-13 | 40
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2024-08-12 | 2024-09-20 | 40
CG 70 | LAKE ERIE | San Diego | CMAV (A) | ACTIVE | 2024-08-12 | 2024-09-22 | 42
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2024-08-12 | 2024-08-30 | 19
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2024-08-13 | 2024-09-20 | 39
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2024-08-19 | 2024-09-27 | 40
DDG 97 | HALSEY | San Diego | CMAV (A) | ACTIVE | 2024-08-26 | 2024-09-13 | 19
LHD 8 | MAKIN ISLAND | San Diego | CMAV (A) | ACTIVE | 2024-10-07 | 2024-11-29 | 54
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2024-10-09 | 2024-11-22 | 45
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2024-10-15 | 2024-11-22 | 39
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2024-10-21 | 2024-12-01 | 42
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2024-10-28 | 2024-12-06 | 40
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2024-11-04 | 2024-12-15 | 42
LSD 52 | PEARL HARBOR | San Diego | CMAV (A) | ACTIVE | 2024-11-10 | 2024-12-30 | 51
LCS 30 | CANBERRA | San Diego | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-07 | 44
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2024-12-06 | 2025-01-31 | 57
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-03 | 19
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2024-12-31 | 16
LHD 2 | ESSEX | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## NWRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
CG 65 | CHOSIN | Everett | CMAV (A) | ACTIVE | 2024-02-20 | 2024-04-12 | 53
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2024-03-18 | 2024-04-26 | 40
DDG 102 | SAMPSON | Everett | CMAV (A) | ACTIVE | 2024-04-22 | 2024-05-31 | 40
DDG 100 | KIDD | Everett | CMAV (A) | ACTIVE | 2024-04-29 | 2024-06-07 | 40
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2024-09-30 | 2024-11-08 | 40
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2024-10-01 | 2024-10-25 | 25
DDG 100 | KIDD | Everett | CMAV (A) | ACTIVE | 2024-11-12 | 2024-12-06 | 25
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## HRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2024-02-12 | 2024-03-01 | 19
CG 67 | SHILOH | Pearl Harbor | CMAV (A) | ACTIVE | 2024-03-04 | 2024-04-05 | 33
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2024-03-09 | 2024-04-16 | 39
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2024-03-11 | 2024-04-19 | 40
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2024-03-25 | 2024-04-19 | 26
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2024-04-08 | 2024-05-03 | 26
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2024-05-28 | 2024-06-21 | 25
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-05 | 33
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2024-06-03 | 2024-07-12 | 40
CG 67 | SHILOH | Pearl Harbor | CMAV (A) | ACTIVE | 2024-07-01 | 2024-08-09 | 40
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2024-08-21 | 2024-10-02 | 43
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2024-10-04 | 2024-11-15 | 43
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2024-11-12 | 2024-12-20 | 39
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”